Purpose:

This framework defines the non-negotiable timelines and gating inputs required to launch any supplement SKU. It allows us to work backward from a target launch date and set clear deadlines for design and approvals.

Non-Negotiable Timelines (Fixed)

These durations cannot be materially compressed and define the critical path.

1.  Vitaquest manufacturing: 6–8 weeks (plan to 8 weeks)

2. Packaging production varies slightly depending on package type:
 – Gusset bags: 5 weeks
 – Shrink wrap: 3–4 weeks (plan to 4 weeks)
 
Packaging must be completed before manufacturing can begin
 
3. 3PL receiving, kitting, and launch readiness: ~1 week

Gating Work (Must Be Completed Before Packaging or Production)
This work determines whether we can even start the fixed timelines above.

- Design direction approved

- Design execution completed

- Internal legal review completed

- Vitaquest label review and approval

- Print-ready artwork delivered

These steps should be treated as a single gated phase:
 “Artwork & Label Approval”

Launch Logic (How We Work Backward)
 For any target launch date:

- Subtract 1 week for 3PL readiness

- Subtract 8 weeks for manufacturing

- Subtract packaging lead time (5 weeks gusset / 4 weeks shrink)

- The resulting date is the latest possible print-ready artwork date

- Design and approvals must start far enough ahead of that date to complete without delay- Design completion and approval is the main gating factor

DESIGN START DEADLINES BY SKU

Assumptions used
 • Manufacturing planned at 8 weeks
 • Gusset bags = 5 weeks
 • Shrink wrap = 4 weeks
 • Design + approvals assumed to take ~4–6 weeks
 • Dates below represent “no-slip” deadlines

Longevity Supplement (Gusset Bag)
Target launch: Late April / May (assume May 1)

- Manufacturing must start: ~March 1

- Gusset bags must be ready: ~February 22

- Print-ready artwork due: ~January 18

- Design + approvals must start: Early January

Status implication: Longevity is only feasible for April/May if design starts immediately.

Skin Supplements
Target launch: May / June (assume June 1) Packaging: Shrink wrap

- Manufacturing must start: ~March 25

- Shrink wrap ready: ~March 1

- Print-ready artwork due: ~February 1

- Design + approvals must start: Early January

Status implication: Skin SKUs require design kickoff in January to avoid slipping to late June or July.

Sleep Supplement
Target launch: June / July (assume July 1)Packaging: Shrink wrap

- Manufacturing must start: ~April 25

- Shrink wrap ready: ~April 1

- Print-ready artwork due: ~March 1

- Design + approvals must start: Early February

Status implication: Sleep is feasible if design starts in February; later than that pushes launch to August.

Remaining Supplement SKUs
Target launch: August
 Packaging: Shrink wrap

- Manufacturing must start: ~June 1

- Shrink wrap ready: ~May 1

- Print-ready artwork due: ~April 1

- Design + approvals must start: March