### For Tyler/Yalda Sync

### Key Areas to Align On:

- Project Plan & Timeline:

  - Outline key milestones from now through launch (including pricing finalization, marketing claims, formulary, regulatory, and manufacturing).

  - Identify any potential bottlenecks and dependencies.

- Roles & Responsibilities:

  - Who owns what? Specifically, where do you see your focus vs. what you need from me, Aaron, and marketing?

  - Yalda: Net new product development, future iterations, bringing forward new things.

  - Collaborate: Competitor landscape/research RE marketing claims. Feedback on branding and messaging, product feedback

  - Tyler: Communication with/vendor relationship, checking with Yalda if it errs into clinical side. Driving everything that is needed to get final product in someone’s hands

  - Coordination on pricing (Vitaquest), marketing claims (Peter/Rachel), and formulary finalization.

- Marketing & Positioning:

  - What is needed from marketing to support a successful launch?

  - Messaging framework, customer segmentation, and competitive differentiation.

  - Any initial creative assets or content planning needed now?

- Regulatory & Compliance:

  - Ensure marketing claims are finalized this week.

  - Confirm what needs to be reviewed internally vs. externally.

- Presentation for Aaron & Marketing Team:

  - What should we include in our presentation to ensure buy-in and execution support?

  - Proposed format (deck, brief, etc.) and key decision points.

Here's a structured document based on your supplement project tracker that you can walk through with your team. Each section includes prompts for you to fill in additional details.

# Noom Supplement Project Timeline & Walkthrough Supplement Project Tracker

Target Launch Date: August 15, 2025

## Project Overview

The goal of this initiative is to launch a Noom-branded supplement line focusing on Metabolic Health, Longevity, Sleep, and Skin Health. This document outlines the key milestones, responsibilities, and dependencies required to bring the products to market.

We are targeting an August 15th launch, however, it is possible to move this launch up by up to 60 days depending on our packaging sourcing, and supplement sampling process

### What will success look like?

Success will be measured by:
✅ Revenue Growth – Achieving $4.77M+ in supplement revenue by FY 2025
✅ Adoption & Retention – High uptake among Noom Weight/Med users, leading to strong subscription renewal rates (DEFINED AS 60% + renwals)
✅ Gross Margin Targets – Attaining 60% margins through strategic pricing and supplier negotiations
✅ Seamless Merchandising – Successfully integrating supplements into the Noom ecosystem (app, email, coaching, community, freemium pathways)

✅ Strong Project Management – Which will allow Noom to standup new product offerings (Heart Health, Brain Health Etc)

✅ BONUS – A launch before August 15th

## Project Timeline & Key Tasks

### 1. Draft Supplement Formularies

- Owner: Tyler Blake, Yalda Olcott

- Start Date: Jan 15, 2025

- End Date: Jan 25, 2025

- Milestone: Send formulary draft to manufacturers

- Deliverable: Supplement Formulary

- Status: ✅ Completed

- Notes:

  - Awaiting pricing, formulary tweaks, final capsule size

### 2. Finalize Supplement Formularies

- Owner: Yalda Olcott

- Start Date: Jan 31, 2025

- End Date: Feb 7, 2025

- Milestone: Signoff from Leadership Team (LT)

- Deliverable: Supplement Formulary File

- Status: ⏳ In Progress

- Notes:

  - Pricing is determined by final formularies, need to get rough pricing, determine a tentative MSRP, and align

  - How are we ensuring the final formulas align with Noom’s health philosophy?

### 3. Receive Pricing from Suppliers

- Owner: Tyler Blake

- Start Date: Feb 3, 2025

- End Date: Feb 7, 2025

- Milestone: Supplier Deliverable

- Deliverable: Pricing File

- Status: ⏳ In Progress

- Notes:

  - Likely we will go with Vitaquest, pending review from Superior Supplements as well

  - Determine ceiling MSRP. $45 has been target in some modeling, longevity likely can up-charge for

### 4. Finalize Marketing Claims

- Owner: Rachel Mahoney, Peter Scherr, Aaron Severs

- Start Date: Feb 3, 2025

- End Date: Feb 7, 2025

- Milestone: Marketing LT Signoff

- Deliverable: Marketing Claims File

- Status: 🚫 Not Started

- Notes:

  - How do we ensure claims are FDA-compliant and backed by scientific evidence? <- share formulary clinical research Supplement Data Tracker

  - What differentiates our supplement messaging from competitors?

### 5. Finalize Pricing Strategy & Margins

- Owner: Jean Clifton, Tyler Blake

- Start Date: Feb 7, 2025

- End Date: Feb 15, 2025

- Milestone: Pricing Milestone

- Deliverable: Pricing Strategy File

- Status: 🚫 Not Started

- Notes:

  - Creat budget for packaging and shipping scenarios

  - Aligin on gross margin target of 60%>

  - Share VOUS analysis for competitive benchmarking

### 6. Execute Master Services Agreement (MSA) with Supplier

- Owner: Adam Kassner

- Start Date: Feb 14, 2025

- End Date: Feb 20, 2025

- Milestone: Executed MSA

- Deliverable: Signed Agreement

- Status: 🚫 Not Started

- Notes:

  - Any key legal concerns or negotiation points?

    - Likely will look like MSA we have with BPI/TPH

### 7. Begin Product Sampling

- Owner: Tyler Blake

- Start Date: Feb 21, 2025

- End Date: Mar 31, 2025

- Milestone: Final Sample Approval

- Deliverable: Sample Review File

- Status: 🚫 Not Started

- Notes:

  - Need to partner in depth with Vitaquest to understand process

  - How do we ensure final product meets taste, texture, and effectiveness standards?

### 8. Scope Product Sprint Work

- Owner: Aaron Severs

- Start Date: Feb 3, 2025

- End Date: Feb 21, 2025

- Milestone: Clearly Defined Sprint

- Deliverable: Sprint Scope File

- Status: 🚫 Not Started

- Notes:

  - Determine which surfaces we want to prioritize merchandising with and the means to do so

### 9. Submit Packaging Recommendation

- Owner: Tyler Blake

- Start Date: Feb 3, 2025

- End Date: Feb 21, 2025

- Milestone: Branding Kickoff

- Deliverable: Supplement Packaging Insights

- Status: ⏳ In Progress

- Notes:

  - What packaging form factor aligns with Noom’s brand and customer expectations?

    - Can we build consistent look and feel across med and OTC?

### 10. Create & Finalize Branding

- Owner: Russell Der, Fatima Cantos

- Start Date: Feb 10, 2025

- End Date: Mar 21, 2025

- Milestone: Print Ready Files

- Deliverable: Branding Assets

- Status: 🚫 Not Started

- Notes:

  - What are the key design principles for branding?

### 11. Begin Launch Strategy

- Owner: Casey Dubie, Brandyn Bissinger

- Start Date: Mar 21, 2025

- End Date: Apr 30, 2025

- Milestone: Marketing Plan Established

- Deliverable: GTM Strategy Document

- Status: 🚫 Not Started

- Notes:

  - What are our key marketing channels and budget allocations?

  - Influencer strategy, Tiktok shop surfaces etc

### 12. Order Custom Packaging

- Owner: Tyler Blake

- Start Date: Mar 21, 2025

- End Date: May 31, 2025

- Milestone: Receive Packaging at Supplier

- Deliverable: Packaging Order File

- Status: 🚫 Not Started

- Notes:

  - Investigate India/domestic manufacturing here

  - Boxes maybe made INTL

### 13. Establish 3PL

- Owner: Tyler Blake

- Start Date: Feb 14, 2025

- End Date: Apr 30, 2025

- Milestone: Executed MSA, Pharmacy Partner Confirmed

- Deliverable: 3PL Agreement

- Status: 🚫 Not Started

- Notes:

  - Which fulfillment partner will we use for distribution?

  - How will we stand up TPH and HeWa to dispense supplements alongside meds

### 14. Start Manufacturing Run

- Owner: Tyler Blake

- Start Date: Jun 1, 2025

- End Date: Jul 31, 2025

- Milestone: Production Completed

- Deliverable: Manufacturing Confirmation

- Status: 🚫 Not Started

- Notes:

  - Get info from Vitaquest RE manufacturing run expectations, ensure all elements of production, packouts, API etc are on site

### 15. Receive Final Product

- Owner: Tyler Blake

- Start Date: Aug 7, 2025

- End Date: Aug 7, 2025

- Milestone: Product Received

- Deliverable: Product Inspection Report

- Status: 🚫 Not Started

- Notes:

  - Allocate inventory by location

### 16. QA & End-to-End Testing

- Owner: Aaron Severs

- Start Date: Aug 7, 2025

- End Date: Aug 14, 2025

- Milestone: QA Completed

- Deliverable: QA Test Results

- Status: 🚫 Not Started

- Notes:

  - What testing procedures will be followed before launch?

### 17. Launch

- Owner: Tyler Blake

- Date: Aug 15, 2025

- Milestone: Official Launch

- Status: 🚫 Not Started

- Notes:

  - What are the launch day deliverables and team responsibilities?